## Tasks List
Owner | Task | What Needs to Be Done | Status | ETA | Migration Tracker Coverage
Rajinder | Execution Type Transformation | Verify whether Execution Type is already implemented in SQL. Add logic if missing. For Initiatives use Demand Type | Completed | 2026-06-05 | Tracker IDs: Prod-Init-027 ¦ Prod-Init-028 ¦ Prod-Init-029 ¦ Prod-Epic-011 ¦ Prod-Epic-012 ¦ Prod-Epic-017 Prod-Init-027: Rename_ExecutionType_Legacy — rename Execution Type → Execution Type - Legacy Prod-Init-029: Add_Execution_Type — derive Demand Bundle / Business Demand from Demand Type - Legacy Prod-Init-028: Add_Is this demand Business Only? — helper routing field Prod-Epic-011: Rename_ExecutionType_Legacy (Epics) — same legacy rename on Epics Prod-Epic-012: Add_Execution_Type (Epics) — IMR containers → REMOVE; all others → Epic Prod-Epic-017: Add_WorkType (Epics) — derive Work Type from Demand Type - Legacy
Rajinder | Demand Type Transformation | Implement the new Demand Type derivation logic | Completed |  | Tracker IDs: Prod-Init-031 ¦ Prod-Init-014 ¦ Prod-Epic-011 ¦ Prod-Epic-017 Prod-Init-031: Add_Demand_Type — new target Demand Type from Flow Type (Non-Discretionary / Discretionary) Prod-Init-014: Rename_DemandType_Legacy (Initiatives) — legacy rename confirmed complete Prod-Epic-011: Rename_DemandType_Legacy (Epics) — Demand Type → Demand Type - Legacy Prod-Epic-017: Work Type derivation — Business Only → Business Demand; others → Tech-Enabled Intake
Rajinder | Flow Type Validation | Verify latest Flow Type logic and ensure updated values are reflected in output tables. | Completed |  | Tracker IDs: Prod-Init-008 ¦ Prod-Init-009 ¦ Prod-Init-010 ¦ Prod-Init-011 ¦ Prod-Init-012 ¦ Prod-Init-013 ¦ Prod-Init-014 Prod-Init-008: Add_FlowType_Step1 — 6-branch derivation: Demand Type + BC flag + Demand SubType Prod-Init-009: #Replaced Value_EAV — remap legacy 'zz' EAV labels + renumber 2→1, 3→2, 4→3 Prod-Init-010: Add_ValueRange_Step1 — NRB Exit Rate 2028 → EVR thresholds (<$1M / $1–10M / >$10M) Prod-Init-011: Add_ValueRange_Step2 — L1 Net Recurring Benefits P&L/Hard → EVR thresholds Prod-Init-012: Add_ValueRange_Step3 — passthrough from cleaned EAV source; null → Unknown Prod-Init-013: Add_ValueRange_Consolidated — waterfall Step1→Step2→Step3; removes 5 temp fields Prod-Init-014: Add_FlowType_Final — resolve TBD rows via T-Shirt + EVR Consolidated
Rajinder | Stage Validation | Verify Stage mapping logic and confirm fixes (e.g., L5 issues). | Completed | 2026-06-04 | Tracker IDs: Prod-Init-006 ¦ Prod-Init-007 ¦ Prod-Init-015 ¦ Prod-Epic-013 Prod-Init-006: Add_Disposition — flag Exclude from Migration / L0-SL1 / LE-LM rows as Remove Prod-Init-007: Remove_Disposition — delete Remove rows before Stage derivation Prod-Init-015: Add_Stage_New / RemoveOldStage / RenameTransformedStage — full Stage matrix all Demand Types × Flow Types; Stage_Original preserved as audit column Prod-Epic-013: Transform_Stage (Epics) — LM/LE: I/J/K/SL5/L5→I:L4, G/H/SL4→G:L3; non-LM/LE→null. Prod-Init-016: Add_SL3_EPG through Add_SL4_CloseWB — 16 approval/review columns derived from Stage (G:L3 → SL3+L3 fields approved; I:L4 → all including SL4; C:L1 and E:L2 → null). ALL 16 columns required for Dev upload. SL2 blocks NOT implemented.
Rajinder | Line Break & Special Character fix | Verify SQL outputs preserve carriage returns, line feeds, and paragraph formatting. | Completed | 2026-06-05 | Tracker IDs: None — no tracker step ID exists yet No dedicated tracker step in Migration_Transformation_Tracke for this issue Affects: Description, Notes, Comments and all rich-text fields written through SQL pipeline Investigation scope: (1) SQL load stage (2) SP transformation (3) Planview export/import Related: Bert — Line Break Investigation (Row 22 in this tracker) Action: raise a new tracker entry once root cause confirmed
Rajinder | Completed Earlier |  | Completed |  | Tracker IDs: Prod-Init-017 ¦ Prod-Init-018 ¦ Prod-Init-021 ¦ Prod-Init-023 ¦ Prod-Init-024 ¦ Prod-Init-025 ¦ Prod-Init-009 ¦ Prod_Init_Rename (bulk) ¦ Rename_DemandType_Legacy ¦ Prod-Epic-005 ¦ Prod-Epic-010 ¦ Prod-Epic-020 ¦ Epic_Rename (bulk) ¦ MilestoneType (SP1 Mappings 6 & 13) ── Initiatives ── Prod_Init_Rename (bulk) ¦ SP1 – Rename section: All Initiative source columns renamed to Dev target names Rename_DemandType_Legacy ¦ SP1 – Rename section: Demand Type → Demand Type - Legacy Prod-Init-009 ¦ SP1 – Mapping 3: EAV renumber — remap 'zz' prefixed labels; renumber 2→1, 3→2, 4→3 Prod-Init-017 ¦ SP1 – Mapping 4: WR43_wbs155_HomePortfolio — 'Data & AI' → 'Platforms' Prod-Init-018 ¦ SP1 – Mapping 7: Add_Work_Type — Tech-Enabled Intake / Business Demand from Demand Type Prod-Init-021 ¦ SP1 – Mapping 9: RemoveDomainFromValue + WR40_Domain_BU — strip ' Domain' suffix; copy to BU lookup column Prod-Init-023 ¦ SP1 – Mapping 2: Work Status mapping — 9-value Lifecycle Status → Work Status incl. Assumed Completed → Completed/Closed Prod-Init-024 ¦ SP1 – Mapping 10: WR31¦wbs154_Confidential — Confidential/Ultra-Confidential → 'Yes - Privileged & Confidential' Prod-Init-025 ¦ SP1 – Mapping 5: WR53_DemandSubType + RiskSubType — normalize Demand SubType; copy to Risk Subtype field ── Epics ── Epic_Rename (bulk) ¦ SP1 – Rename section: All Epic source columns renamed to Dev target names Prod-Epic-005 ¦ SP1 – Mapping 3: EAV renumber — same renumbering applied to Epics sheet Prod-Epic-010 ¦ SP2 – Order 0.2: Establish_Prod_Epic_Index — generate Index_ID key: Prod-Epic-XXXX Prod-Epic-020 ¦ SP1 – Mapping 12: WBS86 Governance Level — PEL → 'Portfolio Execution Leadership'; Solution/empty → null ── Tasks ── MilestoneType ¦ SP1 – Mappings 6 & 13: Task/Milestone Type mapping — Technology / Finance / Legal / Regulatory → consolidated values
Bert | Rosetta Stone SQL Logic | Review Rosetta Stone/logic and write remaining business rules into SQL. | In Progress | 2026-06-08 | Tracker IDs: RosettaStone-001 ¦ RosettaStone-002 ¦ RosettaStone-003 ¦ RosettaStone-004 ¦ RosettaStone-005 ¦ RosettaStone-006 ¦ RosettaStone-007 ¦ RosettaStone-008 RS-001: Result (Table.Combine) — UNION ALL 10 sources into consistent column shape RS-002: Add_Unified_SeqID — COALESCE Strategy Seq ID ¦ Sequence ID RS-003: Add_New_Sequence_ID — LEFT JOIN Dev_PPL_0_Source on Index = Previous Seq_ID; ERROR-NO MATCH if unresolved RS-004: Add_Parent_Index — large CASE WHEN per Data Source establishing parent chain for every entity RS-005: Epic_Disposition_Join — cascade Initiative Disposition → child Epics RS-006: Task_Disposition_Join — cascade Epic Disposition → child Tasks RS-007: Recombine_With_Disposition — UNION ALL 4 branches into final RosettaStone table RS-008: DQ Index uniqueness check — zero duplicate Indexes required
Bert | Hierarchy Support Fields | Ensure SQL outputs contain all identifiers needed by migration (Work Sequence ID, Parent IDs, External Keys, etc.). | In Progress | 2026-06-08 | Tracker IDs: RS-Source-001 ¦ RS-Source-002 ¦ RS-Source-003 ¦ RS-Source-004 ¦ RS-Source-005 ¦ RS-Source-006 ¦ RS-Source-007 ¦ RS-Source-008 ¦ Reference-001 RS-Source-001: Prod_Init_Source — Name, Data Source, Index, Strategy Seq ID, Parent Seq ID, Disposition, Demand Type RS-Source-002: Prod_Epic_Source — raw load + Index = Prod-Epic-+Sequence ID RS-Source-003: Prod_EpicLMLEPPL0_Source — LM/LE Epics at PPL+0 → D&T Cross-Portfolio Demand RS-Source-004: Prod_Task_Source — filter PATH IS NOT NULL + Index RS-Source-005: SBA_ExecutionPackages_Source — Parent Seq ID = SBA-VB-+Work Seq ID RS-Source-006: SBA_Tasks_Source — strips 4 prefixes; Parent Index = SBA-ExP-+Parent Seq ID RS-Source-007: Dev_PPL_0_Source — CRITICAL REFRESH after Phase 1 upload RS-Source-008: Dev_PPL_1_Source — CRITICAL REFRESH after Phase 2 upload Reference-001: load_work_hierarchy — fill-down Lvl2, strip parenthetical suffixes, Freight fix
Bert | Rosetta Stone Review | Review and understand business logic, hierarchy rules, and migration approach. | In Progress | 2026-06-08 | Tracker IDs: RosettaStone-001 to -008 ¦ Phase-Gate-001 ¦ Phase-Gate-002 RosettaStone-001 to -008: Full understanding of UNION ALL 10 sources + NEW DEV SEQUENCEID join + Parent Index logic Phase-Gate-001: Dev_PPL_0_Source MUST be refreshed after Phase 1 before any Phase 2 queries run Phase-Gate-002: Dev_PPL_1_Source MUST be refreshed after Phase 2 before Phase 3 runs Key design rules: MUST use JOIN not row-by-row (60k+ rows); zero duplicate Indexes required Disposition cascade: Prod-Init → Prod-Epic → Prod-Task via join-based logic
Bert | Elevated Epic Creation | Create elevated Lifecycle Management and Local Enhancement epics in target hierarchy. | In Progress | 2026-06-08 | Tracker IDs: LM/LE-Elev-001 ¦ LM/LE-Elev-002 ¦ LM/LE-Elev-003 ¦ LM/LE-Elev-004 ¦ LM/LE-Elev-005 ¦ LM/LE-Elev-006 ¦ LM/LE-Elev-007 ¦ LM/LE-Elev-008 ¦ LM/LE-Elev-009 Elev-001: Filter_LM_LE — filter Execution Type - Legacy IN (Lifecycle Management Epic, Local Enhancement Epic) Elev-002: RemoveGrandParentandParent — remove PPL+2 parent columns before PPL+0 parent is set Elev-003: Update_DataSource — override to Prod-EpicLMLEPPL0 Elev-004: Update_Index — replace Prod-Epic- prefix with Prod-EpicLMLEPPL0- (must match RS-Source-003) Elev-005: Add_Parent_Sequence_ID — scalar lookup of D&T Cross-Portfolio Demand Seq ID; apply as constant Elev-006: Add_Execution_Type — override to Demand Bundle Elev-007: Add_ArchitecturePM — PLACEHOLDER USERNAME constant Elev-008: Add_Demand_Type — Non-Discretionary / Discretionary from Flow Type Elev-009: Add_Prev_SequenceID — duplicate Index as Previous Seq_ID
Bert | PPL Hierarchy Creation | Build PPL+0, PPL+1, and PPL+2 structures in target environment. | In Progress | 2026-06-08 | Tracker IDs: Create-PPL0-001 ¦ Create-PPL1-001 ¦ Create-PPL2-001 ¦ Reference-012 ¦ Reference-013 ¦ Phase-Gate-001 ¦ Phase-Gate-002 Create-PPL0-001: Create_PPL_0_All — UNION: Prod Init active + SBA VBs + LM/LE Elevator; apply PPL_0_Remover Create-PPL1-001: Create_PPL_1_All — synthetic EPs for each Prod PPL+0 item + SBA EPs; requires Phase 1 + RS refresh Create-PPL2-001: Create_PPL_2_All — active Epics + Prod Tasks + SBA Tasks; requires Phase 2 + Dev_PPL_1_Source refresh Reference-012: load_ppl0_remover — final column removal applied AFTER combine Reference-013: load_ppl2_remover — final column removal for PPL+2 Phase-Gate-001 & -002: HARD BLOCKERS — no PPL+1 or PPL+2 can be validated until respective phases uploaded
Bert | Parent-Child Relationships | Create and validate hierarchy links between work items, execution packages, epics, and tasks. | In Progress | 2026-06-08 | Tracker IDs: RosettaStone-004 ¦ Prod-Init-022 ¦ Prod-Epic-006 ¦ Prod-Epic-007 ¦ Prod-Epic-008 ¦ Prod-Task-004 ¦ Prod-Task-005 ¦ Prod-Task-007 ¦ SBA-ExP-001 ¦ SBA-Tasks-003 RosettaStone-004: Add_Parent_Index — parent chain for every entity (10 Data Source branches) Prod-Init-022: Add_Parent_Sequence_ID — TWO separate joins: non-BO (D&T node name) + BO (Lvl2+BU match) Prod-Epic-006: Joined_Parent_Index — LEFT JOIN RS on Associated Initiative Seq ID = Unified Source Seq ID Prod-Epic-007: Add_GrandParent_Index — LM/LE → Prod-EpicLMLEPPL0- prefix; others → parent Init Index Prod-Epic-008: Add_Parent_SeqID_Final — JOIN GrandParent Index to Dev_PPL_1_Source Prod-Task-004: Convert_Parent_To_Epic_Index — prepend Prod-Epic- to raw Parent Sequence ID Prod-Task-005: Join_Parent_Epic — LEFT JOIN RS Prod-Epic rows; COALESCE null GrandParent Index Prod-Task-007: Add_Parent_SeqID_Final (Tasks) — JOIN GrandParent Index to RS for NEW DEV SEQUENCEID SBA-ExP-001: Add_Parent_Sequence_ID — SBA-VB-+Work Seq ID SBA-Tasks-003: Add_Parent_SeqID — JOIN Parent Index to RS Index
Bert | Consume SQL Outputs | Load Rajinder's latest transformed data into Sandbox/Dev environment. | In Progress | 2026-06-08 | Tracker IDs: DQ-Check-001 ¦ DQ-Check-002 ¦ DQ-Check-003 DQ-Check-001: Prod-Init Index uniqueness — zero duplicates before consuming DQ-Check-002: Prod-Epic Index uniqueness — zero duplicates before consuming DQ-Check-003: Upload file row count reconciliation — verify counts before each upload phase SP output: dbo.Planview2026PlatinumConsolidatedUpdated returns 6 result sets (Initiatives, Epics, counts, change tracking, deleted rows, changes detail)
Bert | Validation Extract Creation | Generate PPLK+0, PPL+1, and PPL+2 extracts for validation. | In Progress | 2026-06-08 | Tracker IDs: DQ-Check-003 ¦ DQ-Check-004 ¦ DQ-Check-005 ¦ Create-PPL0-001 ¦ Create-PPL1-001 ¦ Create-PPL2-001 DQ-Check-003: Upload file row count reconciliation — PPL+0 / PPL+1 / PPL+2 expected counts formula DQ-Check-004: Null/ERROR Parent Seq ID check — must be zero before uploading each phase DQ-Check-005: RosettaStone resolution rate — tracks resolved vs unresolved NEW DEV SEQUENCEIDs by entity type Create-PPL0/1/2-001: the three upload tables ARE the validation extracts
Bert | Add Missing Columns | Add Work Parent, Work Name, Execution Type, Parent Sequence IDs, etc. to extracts. | In Progress | 2026-06-08 | Tracker IDs: Reference-001 ¦ Prod-Init-005 ¦ Prod-Init-035 ¦ Prod-Epic-005 ¦ Prod-Epic-025 ¦ Prod-Init-022 ¦ Prod-Epic-008 ¦ RosettaStone-003 Reference-001: load_work_hierarchy — Normalized Name, Normalized Sequence ID, Lvl2, Level, Data Source, Index Prod-Init-005: CreateIndex — Index = Prod-Init-+Strategy Seq ID Prod-Init-035: Add_Prev_SequenceID — duplicate Index as Previous Seq_ID (Initiatives) Prod-Epic-005: Add_Index — Index = Prod-Epic-+Sequence ID Prod-Epic-025: Duplicate_Index_to_PreviousSeqID — Previous Seq_ID for Epics Prod-Init-022: Add_Parent_Sequence_ID — Work Sequence ID / Parent Sequence ID for Initiatives Prod-Epic-008: Parent Sequence ID (Dev EP Seq ID) for Epics RosettaStone-003: NEW DEV SEQUENCEID — join-based lookup for all entities
Bert | Reconciliation Support | Produce extracts for comparison between source and target systems. | In Progress | 2026-06-09 | Tracker IDs: Inv-Dep-001 ¦ Inv-Dep-002 ¦ Inv-Dep-003 ¦ Inv-Dep-004 ¦ Inv-Dep-005 ¦ Inv-Dep-006 ¦ Inv-Dep-007 ¦ Inv-Dep-008 ¦ DQ-Check-005 Inv-Dep-001: build_inv_dep_base — UNION PPL+0 sources; keep Investment Dependencies, Work Name, Index; filter non-null Inv-Dep-002: split_inv_dep_semicolon — split semicolon-delimited field into individual rows; TRIM required Inv-Dep-003: split_inv_dep_colon — split each entry on ': ' into type + Enabled Name Inv-Dep-004: filter_inv_dep_types — keep Co-Dependent With and Required By only Inv-Dep-005: join_inv_dep_enabled — LEFT JOIN RS by Enabled Name; flag ERROR-NO MATCH Inv-Dep-006: filter_inv_dep_invalid — remove ERROR-NO MATCH rows Inv-Dep-007: add_inv_dep_source_seq_id — JOIN source Index to RS for Source NEW DEV SEQUENCEID Inv-Dep-008: reorder_inv_dep_cols — final 7-column reference output (not a direct upload file) DQ-Check-005: RosettaStone resolution rate by Data Source and phase
Bert | Line Break Investigation | Determine whether formatting loss occurs during export, import, or within Planview. | In Progress | 2026-06-08 | Tracker IDs: None — no tracker step ID exists yet No dedicated tracker step in Migration_Transformation_Tracke for this issue Investigation scope: (1) SQL load stage (2) SP transformation (3) Planview export/import Related: Rajinder — Line Break & Special Character fix (Row 10 in this tracker) Action: raise a new tracker entry once root cause confirmed Note: Not in Migration_Transformation_Tracke
Bert | Implement SBA Migration Design | Extract SBA records, apply approved Rosetta Stone hierarchy and lifecycle movement guidance, configure target Planview structures as required, and validate successful loading and placement in the target environment. | Pending | 2026-06-09 | Tracker IDs: SBA-VB-001 to SBA-VB-013 ¦ SBA-ExP-001 ¦ SBA-ExP-002 ¦ SBA-Tasks-001 ¦ SBA-Tasks-002 ¦ SBA-Tasks-003 ¦ SBA-Tasks-004 ¦ RS-Source-005 ¦ RS-Source-006 ¦ Reference-014 ¦ Reference-015 SBA-VB-001 to -013: Full SBA Value Bundle pipeline — column keep, date cast, Index = SBA-VB-+Seq ID, delimiter fix, Templates filter, WORK_HIERARCHY parent join (Level=4 critical), bulk rename, Arch PM placeholder, Demand Type = Program Value Bundle, Final Removals SBA-ExP-001: Add_Parent_Sequence_ID — Parent = SBA-VB-+Work Seq ID SBA-ExP-002: Rename + Previous Seq_ID from Index SBA-Tasks-001: Transform_Task_Milestone_Type — same mapping as Prod Tasks SBA-Tasks-002: Transform_Work_Status — same as Prod Tasks + 3 extra SBA-specific values SBA-Tasks-003: Add_Parent_SeqID — JOIN Parent Index to RS Index SBA-Tasks-004: Add_Prev_SequenceID — duplicate Index as Previous Seq_ID RS-Source-005 & -006: SBA EP + Tasks sources feeding RosettaStone Reference-014: load_sba_rename ¦ Reference-015: load_sba_vb_remover_late
Julian | Define Validation Scope | Create validation checklist and reconciliation criteria. | Pending
Julian | Source vs Target Validation | Compare Production extracts with Sandbox/Dev extracts. | Pending
Julian | Identify Missing Attributes | Review extracts and identify missing columns or data. | Pending
Julian | Validate SBA hierarchy placement after load | Validate hierarchy placement in target Planview confirm correct portfolio, program, value bundle work parent, and parent child relationship. | Pending
Julian | Validate SBA lifecycle placement after load | Validate SBA lifecycle placement in target Planview against approved migration rules and confirm records are loaded in to the correct lifecycle stages | Pending
Julian | SBA reconciliation (source vs target counts) | Reconcile SBA source and target record counts and identify any missing, duplicate unmatched records | Pending
Julian | Hierarchy Validation | Validate hierarchy placement in target Planview and confirm records are loaded in to the correct portfolio, program, value bundle, work parent and parent child structure | Pending
Julian | Lifecycle Placement Validation | validate target lifecycle placement per approved lifecycle movement guidance. | Pending
Julian | Mock0 Reconciliation | Reconcile source, transformed, and target records for Mock0 and document variances. | Pending
Julian | Mock0 Signoff Report | Document Mock0 results, findings, open issues, and readiness recommendation for Mock1. | Pending