## Tasks List
Owner | Task | What Needs to Be Done | Status | ETA
Rajinder | Execution Type Transformation | Verify whether Execution Type is already implemented in SQL. Add logic if missing. For Initiatives use Demand Type | In Progress | 2026-06-05
Rajinder | Demand Type Transformation | Implement the new Demand Type derivation logic | Completed
Rajinder | Flow Type Validation | Verify latest Flow Type logic and ensure updated values are reflected in output tables. | Completed
Rajinder | Stage Validation | Verify Stage mapping logic and confirm fixes (e.g., L5 issues). | Completed | 2026-06-04
Rajinder | Line Break & Special Character fix | Verify SQL outputs preserve carriage returns, line feeds, and paragraph formatting. | In Progress | 2026-06-05
Bert | Rosetta Stone SQL Logic | Review Rosetta Stone/logic and write remaining business rules into SQL. | In Progress | 2026-06-08
Bert | Hierarchy Support Fields | Ensure SQL outputs contain all identifiers needed by migration (Work Sequence ID, Parent IDs, External Keys, etc.). | In Progress | 2026-06-08
Bert | Rosetta Stone Review | Review and understand business logic, hierarchy rules, and migration approach. | In Progress | 2026-06-08
Bert | Elevated Epic Creation | Create elevated Lifecycle Management and Local Enhancement epics in target hierarchy. | In Progress | 2026-06-08
Bert | PPL Hierarchy Creation | Build PPL+0, PPL+1, and PPL+2 structures in target environment. | In Progress | 2026-06-08
Bert | Parent-Child Relationships | Create and validate hierarchy links between work items, execution packages, epics, and tasks. | In Progress | 2026-06-08
Bert | Consume SQL Outputs | Load Rajinder's latest transformed data into Sandbox/Dev environment. | In Progress | 2026-06-08
Bert | Validation Extract Creation | Generate PPLK+0, PPL+1, and PPL+2 extracts for validation. | In Progress | 2026-06-08
Bert | Add Missing Columns | Add Work Parent, Work Name, Execution Type, Parent Sequence IDs, etc. to extracts. | In Progress | 2026-06-08
Bert | Reconciliation Support | Produce extracts for comparison between source and target systems. | In Progress | 2026-06-09
Bert | Line Break Investigation | Determine whether formatting loss occurs during export, import, or within Planview. | In Progress | 2026-06-08
Bert | Implement SBA Migration Design | Extract SBA records, apply approved Rosetta Stone hierarchy and lifecycle movement guidance, configure target Planview structures as required, and validate successful loading and placement in the target environment. | Pending | 2026-06-09
Julian | Define Validation Scope | Create validation checklist and reconciliation criteria. | Pending
Julian | Source vs Target Validation | Compare Production extracts with Sandbox/Dev extracts. | Pending
Julian | Identify Missing Attributes | Review extracts and identify missing columns or data. | Pending
Julian | Validate SBA hierarchy placement after load | Validate hierarchy placement in target Planview confirm correct portfolio, program, value bundle work parent, and parent child relationship. | Pending
Julian | Validate SBA lifecycle placement after load | Validate SBA lifecycle placement in target Planview against approved migration rules and confirm records are loaded in to the correct lifecycle stages | Pending
Julian | SBA reconciliation (source vs target counts) | Reconcile SBA source and target record counts and identify any missing, duplicate unmatched records | Pending
Julian | Hierarchy Validation | Validate hierarchy placement in target Planview and confirm records are loaded in to the correct portfolio, program, value bundle, work parent and parent child structure | Pending
Julian | Lifecycle Placement Validation | validate target lifecycle placement per approved lifecycle movement guidance. | Pending
Julian | Mock0 Reconciliation | Reconcile source, transformed, and target records for Mock0 and document variances. | Pending
Julian | Mock0 Signoff Report | Document Mock0 results, findings, open issues, and readiness recommendation for Mock1. | Pending